Handover — EPQPL Cell-Based PM System

Cell-Based PM Planning, Scheduling & Tracking System

Eaton Power Quality Pvt Ltd  ·  Pondicherry  ·  Maintenance Engineering

SharePoint Online  ·  Microsoft Forms  ·  Power Automate  ·  Power BI

No additional licence required

One document. Read this first; everything else is detail it points at.

| What it is | Preventive maintenance planning, scheduling and execution for the Pondicherry fuse plant |
| --- | --- |
| Runs on | SharePoint Online, Microsoft Forms, Power Automate, Power BI — all Microsoft 365 E3 |
| Extra licence cost | None |
| Status | Built and verified against 12 months of data. Not yet provisioned to a live site |
| Effort to go live | About 5 working days, plus 1 day UAT |
| Repository | pm-system/ — 644 files |

## 1. What the system does

Ten rules. They are fixed — the build implements them, it does not reinterpret them.

- PM is triggered per CELL, not per machine. A cell is 3–4 machines.

- The trigger is 4,000 production standard hours accumulated by that cell since its last PM — held per cell in PM_Trigger_Hours, never hard-coded.

- Calendar backstop at 6 months. Whichever comes first wins.

- Amber warning at 90% (3,600 h) so planning has lead time.

- Actual hours arrive monthly — one file, one row per cell — and are added to the cell's running counter.

- The counter resets to zero only when the cell's work order completes.

- A work order holds one task per machine. It closes only when every machine task is done. Three of four is not done.

- Technicians share one M365 login, so a mandatory technician dropdown on every form is the entire audit trail.

- Every machine carries a QR sticker that opens that machine's hub.

- A PM reset falling mid-month prorates that month's hours by working days.

### The one number to watch

`Breakdowns After PM (7d)` — breakdowns on a cell within seven days of a completed PM on that same cell.

Compliance can read 100% while this climbs. When it does, the checklist is being signed rather than performed, or it is checking the wrong things. It is the only measure that tells you whether the PM is real.

On the 12 months of data supplied: 7 of 88 breakdowns (8.0%), carrying 28.1 of the 299.5 hours of annual production loss. Read it as a share, not a count.

This figure was 9 (10.2%) in the first build. A PM is now dated from the latest

machine scan on its work order, rather than from a stored Actual_End_Date column.

In the supplied data those two disagreed on 29 of the 43 completed work orders —

always with the stored date a day or two *later* than the last machine scanned out —

and two breakdowns fell inside the seven-day window only on the strength of that gap.

On-time performance moved the same way, from 48.8% to 65.1%.

**Flow 5 stamps a work order complete in the same run that sees its last machine

task finish**, so the system as built cannot produce a lag of days. That points to

the lag being an artefact of how the sample data was generated. But **if a work

order really is signed off a day or two after the last machine at your plant, that

is a business rule this build does not implement — raise it before go-live.**

ASSUMPTIONS.md §9.1 has the full working.

Either way the two values can no longer disagree, because there is now only one of

them. That is the case for the reduction in one number: a stored rollup had already

drifted from the rows it summarised, in the measure the system's credibility rests

on, and nothing anywhere reported it.

## 2. What has been built

| Component | Contents |
| --- | --- |
| SharePoint | 14 lists, 138 columns, 5 document libraries, 11 views, 7 column-formatting files |
| Data | 2,422 rows, typed and validated, ready to load |
| Power BI | 15 tables, 30 relationships, 85 measures, 9 pages, 116 visuals, custom theme |
| Power Automate | Build sheets for 9 flows, every expression written out |
| QR labels | 30 labels, 50×30 mm, tested; printable A4 sheets |
| Forms | 5 forms, every question listed with the column it lands in, plus the pre-filled-link procedure |
| Documentation | Runbook, assumptions, 36 UAT cases, 1-page bilingual shop-floor SOP |
| Power Apps | Phase 2 spec + licence business case (not licensed today) |

### Data loaded per list

Cell_Master              8      PM_WorkOrder            51

Technician_Master        6      PM_Machine_Task        193

Spare_Master            15      Checklist_Response     997

Checklist_Master        51      Breakdown_Log           88

Machine_Master          30      Spare_Replaced          58

Plant_Calendar         730      Abnormality_Log         44

StdHours_Monthly        96      PM_Plan_Calendar        55

------

2,422

## 3. Decisions of record

All eight open questions are answered. These are settled — do not re-litigate them without a reason, and record the reason if you do.

| # | Question | Decision |
| --- | --- | --- |
| 1 | Do cancelled work orders count against compliance? | No — excluded from PM Due Count |
| 2 | Does a skipped machine block cell closure? | No — the cell closes, flagged partial |
| 3 | Is Actual_Std_Hours an actual or a capacity figure? | Capacity — so proration is by working days |
| 4 | Is the Tamil label wording right? | Yes — approved for print |
| 5 | Are Power Apps rights available? | No — go live on Forms; canvas app is Phase 2 |
| 6 | Who owns the nine flows? | An individual account — see §6, this needs managing |
| 7 | Retention on the transaction lists? | None — keep everything |
| 8 | Is 4,000 hours right for every cell? | Held per cell; all eight currently 4,000 |

Full reasoning and consequences: docs/ASSUMPTIONS.md §8.

### The two that changed the build

Q3 — capacity, not actual. Capacity accrues on the days the plant runs, so a mid-month PM reset prorates by working days. Verified: CELL-05, April 2026, 780 h reported, reset on the 2nd → 24 of 26 working days → 720.00 h posted. Calendar-day proration would have posted 728.00 h — 8 hours the plant was closed for. Small once; it compounds every cycle in the same direction.

This added Plant_Calendar, the 16th list.

Q5 — no Power Apps licence. The system goes live on Forms. Nothing in the data model, the flows or the report depends on the canvas app.

## 4. Going live — the five days

Two guides, same journey:

- `docs/STEP_BY_STEP_GUIDE.md` — plain English, stage by stage, every command written out, no assumed SharePoint or Power BI knowledge. Give this to whoever is doing the build.

- `docs/IMPLEMENTATION_RUNBOOK.md` — the same steps with the full technical detail. Go here when the guide is not specific enough.

The shape of it:

| Day | Step | What happens |
| --- | --- | --- |
| 1 (am) | 1 | Prepare and validate the data — must show 0 errors |
| 1 (pm) | 2–3 | Provision SharePoint, load the data, reconcile row counts |
| 2 | 4 | Build the 5 Forms and the pre-filled links |
| 2 (pm) | 5 | Print, fit and individually scan-test the 30 QR labels |
| 3–4 | 6 | Build the 9 flows |
| 5 (am) | 7 | Open and publish the Power BI report |
| 5 (pm) | 8 | UAT — all 36 cases |
| 6 | 9 | Train, then go live on a Monday |

### Six things that will cost you a day each if you skip them

- Always `-WhatIf` first. All three PowerShell scripts dry-run without touching the tenant and without needing the PnP module installed.

- Check one column's internal name after provisioning. It must read Field=Cell_ID, not Field=Cell%5Fx005f%5FID. A mangled name breaks every query, expression and model reference, silently.

- Reconcile row counts after loading. A short list is a silently dropped row and it will not announce itself later.

- Mark your holidays in `Plant_Calendar` before the first monthly upload. It is seeded with Sundays off only — Pongal, Diwali and the annual shutdown are not guessed. Every unmarked holiday is a day the proration thinks you were running.

- In the Forms, hidden pre-filled fields come FIRST. Machine_ID is always question 1, Cell_ID always question 2. Pre-fill populates by position; insert a question above them later and every sticker on the floor fills the wrong field.

- Run `--test` before printing stickers. A wrong sticker takes a month to surface, by which time it has been scanned two hundred times against the wrong machine.

### Build the flows in this order

1, 2 and 5 are the spine — the counter, the trigger and the reset. Build and test those three before anything else.

Turn concurrency OFF on flows 1 and 5. Both read a value, change it and write it back. Two parallel runs would each read the same counter and one increment would be lost — the first month two cells finish on the same afternoon.

## 5. Before you can call it live

Go-live is blocked until every CRITICAL UAT case passes. 18 of the 35 are critical. These five matter most:

| Case | What it proves |
| --- | --- |
| UAT-14 | Three of four machines complete and nothing resets |
| UAT-15 | The fourth completes and all three Cell_Master fields move in one version |
| UAT-19 | A mid-month reset prorates by working days to 720.00 h — not 780, not 728 |
| UAT-21 | A duplicate month upload is rejected and terminates as Failed |
| UAT-30a | The Monday heartbeat arrives on a clean week |

UAT-14 and UAT-15 together are the whole system. If the counter resets at three of four, every PM interval is wrong from that day on and nothing on any dashboard will show it.

## 6. The one live risk, and how it is managed

The nine flows are owned by an individual account. No service account is available. This works — but the failure mode is silent, so it is managed rather than ignored.

### What actually breaks

A flow has owners and it has connections. Co-owners can edit and repair it. The connections belong to the single account that created them — SharePoint, Outlook, Forms, Teams, Approvals. When that account is disabled or unlicensed, every connection breaks and all nine flows stop, regardless of who else owns them.

Co-ownership shortens the repair. It does not prevent the failure. So the question is not "can someone fix it" but "how long before anyone notices".

### The answer: the Monday heartbeat

Flow 9 sends the daily digest only when something is outstanding — otherwise it stops being read within a fortnight. But that makes silence ambiguous: an empty inbox means either "nothing outstanding" or "the flows died three weeks ago".

So Flow 9 also sends every Monday when clean, as a one-line *"PM system healthy — nothing outstanding"*.

If no digest arrives on a Monday, the flows have stopped.

That is the entire early-warning system. It costs one email a week. Put this

sentence in front of whoever monitors the system.

### Three things to do while building, not after

- Add two named co-owners to every flow. Flow → Share → add both.

- Point every failure branch at a shared mailbox, not the owner's inbox. The built-in "email me if a flow fails" only reaches the owner — no use the day the owner's account *is* what broke.

- Export a flow package after UAT (Power Automate → Export → Package) and keep the .zip with the repository. If the account is ever deleted rather than just unlicensed, the flows go with it.

### When the owning person changes role or leaves

Do it before the leaving date — once the licence is gone the connections are already broken. Full procedure in ASSUMPTIONS.md §8.2. Budget half a day; it is roughly thirty connector steps across nine flows.

## 7. Who does what, ongoing

| When | What | Who |
| --- | --- | --- |
| Every Monday | Confirm the heartbeat digest arrived. No digest = flows stopped | Supervisor |
| Daily | Act on the digest: overdue cells, open work orders, unscanned machines, high-severity abnormalities, reset failures first | Supervisor |
| 1st–3rd | Upload the std-hours workbook to StdHours_Inbox; check the summary email | Planner |
| 5th | Review cells at 90%+; agree PM dates with production | Supervisor |
| 25th | Freeze next month's plan in PM_Plan_Calendar | Supervisor |
| Monthly | Review every Skip_Reason from the month | Manager |
| Monthly | Review Breakdowns After PM (7d) — is the PM working? | Manager |
| Quarterly | Review the Trigger_Type split. Mostly Calendar Backstop means 4,000 is too high | Manager |
| Quarterly | Review Min_Stock against Stock_At_Request history | Stores |
| Each December | Mark next year's holidays and shutdown in Plant_Calendar | Planner |
| Year 4 | Extend Plant_Calendar past 2027-03-31; check Checklist_Response against the 5,000-item threshold | IT |

Freezing the plan on the 25th is what makes adherence honest. Without it you can measure "did we do it" but never "did we do it when we said we would" — and the second question is the one production cares about.

## 8. Where everything lives

input/                  the three source workbooks + data dictionary (unmodified)

sharepoint/

provision_lists.ps1   14 lists, 138 columns, indexes, 5 libraries

apply_views.ps1       11 views + shop-floor column formatting

load_data.ps1         batched CSV load with type conversion

schema/*.json         one schema per list — the source of truth for the scripts

views/_views.json     view definitions incl. "My Allotted PM List", "Machine Hub"

data/*.csv            import-ready data, validation report, row counts

powerbi/

PM_Dashboard.pbip     open this in Power BI Desktop

m_queries/*.pq        20 commented Power Query scripts — source of truth

dax/measures.dax      85 measures, each with a comment explaining it

README_PowerBI.md     open, refresh, repoint to SharePoint

qr/

generate_qr_labels.py --test decodes every label back to its own machine

labels/               30 PNGs + printable PDF

automate/

FLOW_SPECS.md         all 5 forms and all 9 flows, action by action

expressions.md        every expression, copy-paste ready

powerapps/              Phase 2 — specified and costed, not licensed

docs/

STEP_BY_STEP_GUIDE.md       plain-English build walkthrough

IMPLEMENTATION_RUNBOOK.md   the same steps, full technical detail

ASSUMPTIONS.md              every judgement call, with verified figures

UAT_TEST_CASES.md           36 cases

TECHNICIAN_SOP_1PAGE.md     print, laminate, put at every cell

POWERAPPS_LICENCE_CASE.pptx business case for the Power Apps licence

DATA_DICTIONARY.md          copy of the input dictionary

tools/                  data prep, model build, and the three verification scripts

### If you change something

m_queries/*.pq and dax/measures.dax are the source of truth for the Power BI model. After editing either, with Power BI Desktop closed:

python tools/build_pbip.py       # embeds the queries and measures into TMDL

python tools/build_report.py     # regenerates pages, visuals, theme

python tools/validate_model.py   # every reference must resolve — run this last

## 9. How to prove it still works

Five gates. All runnable now, all currently passing.

python tools/prepare_sharepoint_data.py --strict   # 0 errors, 0 warnings, 2,422 rows

python tools/validate_model.py                     # 0 errors, 0 orphaned measures

python tools/verify_measures.py                    # 68 measures, none blank

python qr/generate_qr_labels.py --test             # 30/30 QR round-trip

pwsh sharepoint/provision_lists.ps1 -SiteUrl <url> -WhatIf   # 0 failures

verify_measures.py recomputes every headline measure in plain Python, independently of the DAX, so the two can be compared rather than one trusted. It hand-works the three calculations the system's credibility rests on: Breakdowns After PM (7d), Projected PM Date, and mid-month proration. Expected values are in ASSUMPTIONS.md §9.

Run these after any change. A measure nobody has checked against a known answer is a number, not a fact.

## 10. Troubleshooting — the ones that actually happen

| Symptom | Cause | Fix |
| --- | --- | --- |
| No digest on a Monday | The flows have stopped | Check My flows for a disabled flow or an "Invalid connection" banner — usually the owning account. ASSUMPTIONS.md §8.2 |
| Counter did not reset after all machines done | Flow 5 failed, or a task is Pending not Completed | Check the run history and the Get items pending tasks filter |
| Two work orders for the same cell | Flow 2's open-WO check missing | Cancel one, fix the condition |
| Counter jumped a whole month after a mid-month PM | Proration not applied | Check Cell_Master.Last_PM_Date is inside the uploaded month, and that Get item cell is the first action in Flow 1's row loop |
| Monthly import fails naming a month | Plant_Calendar has no working days for it | Add the dates and mark working days |
| Proration posts slightly too many hours | Holidays not marked in Plant_Calendar | Mark them — the divisor counts working days only |
| Scan opens a blank hub | QR_Payload_URL points at a renamed view | Re-run apply_views.ps1, update the column, reprint |
| Power BI blank columns after repointing | Mangled column internal names | Recreate those columns from field XML |
| Flow fails "cannot convert null" | A null number in arithmetic | Wrap in float(coalesce(x, 0)) |
| List view threshold error | A filtered column is not indexed | Re-run provision_lists.ps1 — it is idempotent |

## 11. Known limits — stated, not hidden

- One thing must be finished by hand in Power BI Desktop: the drillthrough field on page 5. It cannot be expressed in the file format. It takes under a minute and is in README_PowerBI.md. *(There used to be a second — setting the Gantt offset series to no-fill — which had to be redone on every rebuild. The five measures that faked a Gantt out of a stacked bar came out with the reduction, and that step with them.)*

- The Power BI info panel is a footnote, not a bookmark toggle. It uses 40 px of every page. A footnote cannot be left switched off by whoever used the report last. Conversion steps are in README_PowerBI.md if you prefer a toggle.

- `Checklist_Response` reaches the 5,000-item list view threshold around year 5. Not a storage problem — a query one. The indexes already protect against it; review archiving in year 4.

- QR stickers are printed against the SharePoint hub URL. If Power Apps is licensed later the payload becomes a deep link and all 30 need reprinting. A known, accepted cost of starting on Forms.

- The licence business case deck has not been visually proof-read — the rendering tool was unavailable when it was produced. It opens correctly and passes structural checks; give it one pass before presenting.

- Four things the system deliberately does not record. The schema was cut from 224 columns to 138, and these went with it. None is recoverable from history, so if one matters, reinstate it before go-live:

- The scan that led nowhere — a QR scan against a machine with no open work order. The technician is still told; the fact is no longer filed. This is the first thing to bring back if take-up is ever in doubt.

- Spare approval lead time and stock at the moment of asking — gone with the requisition loop, which duplicated a stores process that already exists.

- **Who *started* a PM**, as distinct from who finished it.

- Make, model and year installed — asset-register detail. Age-versus-breakdown analysis now needs the asset register.

ASSUMPTIONS.md §10 has the full record: the three rules the cuts were made against, what each one bought, and the reason for every one of the 58 columns removed.

- The dummy data is dummy data. Every figure quoted in this handover comes from the 12 months supplied for building and testing. Re-run verify_measures.py against real data once loaded.

## 12. First week checklist

- [ ] Decide which individual account owns the flows and Forms

- [ ] Identify the two co-owners and the shared mailbox for failure alerts

- [ ] Create the SharePoint site

- [ ] Run all three PowerShell scripts with -WhatIf, then for real

- [ ] Reconcile row counts against _ROW_COUNTS.csv

- [ ] Verify one column's internal name is unmangled

- [ ] Mark holidays and the annual shutdown in Plant_Calendar for 12 months

- [ ] Build the 5 Forms — pre-filled fields first, technician dropdown mandatory

- [ ] Test one pre-filled link on a real phone before building all 30

- [ ] python qr/generate_qr_labels.py --base-url <site> --test → 30/30

- [ ] Print on polyester at 100% scale, fit, and scan-test every one

- [ ] Build flows 5, 2, 1 first; concurrency OFF on 1 and 5

- [ ] Two co-owners on all 9 flows, failure branches to the shared mailbox

- [ ] Export the flow package to .zip

- [ ] Publish Power BI, schedule refresh 06:00 and 14:00 IST

- [ ] All 36 UAT cases, recorded with a name and date

- [ ] Print and laminate the SOP at every cell

- [ ] Put *"no Monday digest = flows stopped"* in the handover note

- [ ] Go live on a Monday. Run the first monthly upload with someone watching