## READ ME
Abnormality Log - list seed data
PM Planning, Scheduling & Tracking System
Purpose | Anything not right that is not yet a breakdown. The early-warning layer - raised from a failed checklist task or from a walk-by QR scan.
Data owner | Maintenance Head (list owner)
Update frequency | Continuous - written by the Power App and the flows
SharePoint location | https://<tenant>.sharepoint.com/sites/PMSystem/Lists/Abnormality_Log
Power Query binding | For testing: Excel table 'tblAbnormalities'. In production: SharePoint list connector.
Rules | 1. Severity High triggers an immediate email to the Maintenance Head.
2. A photo is mandatory - the app will not submit without one.
3. Status flows: Open -> In Progress -> Closed. CorrectiveAction is mandatory to close.
4. Ageing is measured from ReportedDate; anything open beyond 30 days appears on the escalation view.
5. This workbook is dummy data for building and testing the dashboard. At go-live, create the SharePoint list from the schema in reference/SharePoint_List_Schemas.xlsx and leave it empty.
Do not | x Rename, reorder or delete columns - the Power BI refresh will break.
x Add blank rows inside the table or notes below the table.
x Merge cells anywhere in the data sheet.
x Change the sheet name or the Excel table name.

## Abnormality_Log
AbnormalityID | Source | SourceRefID | MachineID | MachineName | CellID | CellName | Area | Category | Severity | Description | ReportedByTechID | ReportedByName | ReportedDate | Status | ClosedDate | CorrectiveAction | OwnerFunction | EscalationRequired | PhotoURL
ABN-00001 | PM Checklist | WO-00001 | MC-001 | CNC Lathe TL-01 | CELL-01 | CNC Turning Line A | Machine Shop | Oil / coolant leak | Medium | Task 8: Check hydraulic pressure - outside standard (35 - 40 bar) | TECH-02 | Suresh Babu | 2024-09-06 | Closed | 2024-09-29 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-001_1.jpg
ABN-00014 | PM Checklist | WO-00057 | MC-007 | CNC Lathe TL-05 | CELL-02 | CNC Turning Line B | Machine Shop | Overheating | High | Task 10: Tailstock / chuck clamping pressure - outside standard (18 - 22 bar) | TECH-02 | Suresh Babu | 2024-09-14 | Closed | 2024-09-27 | Corrective action completed and verified | Maintenance | Yes | /sites/PMSystem/Photos/MC-007_14.jpg
ABN-00002 | PM Checklist | WO-00003 | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Loose / missing fastener | Medium | Task 4: Check way lube level and top up - outside standard (Above MIN mark) | TECH-03 | Mohammed Rafi | 2024-09-15 | Closed | 2024-09-27 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-003_2.jpg
ABN-00003 | PM Checklist | WO-00003 | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal vibration | High | Task 10: Tailstock / chuck clamping pressure - outside standard (18 - 22 bar) | TECH-03 | Mohammed Rafi | 2024-09-15 | Closed | 2024-10-02 | Corrective action completed and verified | Maintenance | Yes | /sites/PMSystem/Photos/MC-003_3.jpg
ABN-00015 | PM Checklist | WO-00058 | MC-008 | VMC MC-01 | CELL-02 | CNC Turning Line B | Machine Shop | Abnormal noise | High | Task 12: Check chiller for spindle - temp and level - outside standard (20 +/- 2 deg C) | TECH-01 | Arun Kumar | 2024-09-18 | Closed | 2024-10-17 | Corrective action completed and verified | Production | Yes | /sites/PMSystem/Photos/MC-008_15.jpg
ABN-00016 | PM Checklist | WO-00059 | MC-009 | VMC MC-02 | CELL-02 | CNC Turning Line B | Machine Shop | Air leak | High | Task 2: Clean work enclosure, chip auger and coolant tank - outside standard (No chip accumulation) | TECH-03 | Mohammed Rafi | 2024-09-26 | Open |  |  | Production | Yes | /sites/PMSystem/Photos/MC-009_16.jpg
ABN-00198 | QR Walk-by |  | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Wiring / cable damage | High | Observed during shop floor round - logged via machine QR | TECH-01 | Arun Kumar | 2024-10-07 | Closed | 2024-10-15 | Rectified during next available window | Maintenance | Yes | /sites/PMSystem/Photos/MC-017_198.jpg
ABN-00200 | QR Walk-by |  | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2024-10-07 | Closed | 2024-10-16 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-024_200.jpg
ABN-00115 | QR Walk-by |  | MC-031 | Hyd Press HP-01 | CELL-08 | Press Shop | Fabrication | Corrosion / rust | Low | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2024-10-14 | Closed | 2024-11-01 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-031_115.jpg
ABN-00182 | QR Walk-by |  | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Housekeeping / 5S issue | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2024-10-21 | Closed | 2024-10-22 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-030_182.jpg
ABN-00183 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Oil / coolant leak | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2024-10-25 | Closed | 2024-11-08 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-003_183.jpg
ABN-00199 | QR Walk-by |  | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Warning lamp / alarm active | Medium | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2024-10-25 | Closed | 2024-11-26 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-011_199.jpg
ABN-00202 | QR Walk-by |  | MC-010 | Gear Hobber GH-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Overheating | Medium | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2024-10-31 | Closed | 2024-11-06 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-010_202.jpg
ABN-00127 | QR Walk-by |  | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2024-11-02 | Closed | 2024-11-10 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-016_127.jpg
ABN-00086 | QR Walk-by |  | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2024-11-10 | Closed | 2024-11-22 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-020_86.jpg
ABN-00083 | QR Walk-by |  | MC-027 | Robot Weld Cell RW-01 | CELL-07 | Robotic Welding Bay | Fabrication | Air leak | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2024-11-11 | Closed | 2024-12-18 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-027_83.jpg
ABN-00053 | PM Checklist | WO-00186 | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Safety device bypassed | High | Task 8: Check station lighting and andon - outside standard (>= 500 lux) | TECH-10 | Naveen Raj | 2024-11-13 | Closed | 2024-11-14 | Corrective action completed and verified | Production | Yes | /sites/PMSystem/Photos/MC-020_53.jpg
ABN-00054 | PM Checklist | WO-00188 | MC-022 | Leak Test Rig LT-01 | CELL-05 | Assembly Line 1 | Assembly | Oil / coolant leak | Medium | Task 3: Torque tool calibration verification - outside standard (+/- 3 % of setpoint) | TECH-10 | Naveen Raj | 2024-11-20 | Closed | 2024-12-06 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-022_54.jpg
ABN-00136 | QR Walk-by |  | MC-002 | CNC Lathe TL-02 | CELL-01 | CNC Turning Line A | Machine Shop | Air leak | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2024-11-23 | Closed | 2024-12-07 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-002_136.jpg
ABN-00197 | QR Walk-by |  | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Overheating | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2024-11-27 | Closed | 2024-12-09 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-029_197.jpg
ABN-00124 | QR Walk-by |  | MC-025 | Curing Oven CO-01 | CELL-06 | Paint & Finishing | Finishing | Damaged guard or cover | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2024-12-04 | Closed | 2024-12-08 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-025_124.jpg
ABN-00213 | QR Walk-by |  | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2024-12-15 | Closed | 2024-12-31 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-011_213.jpg
ABN-00078 | QR Walk-by |  | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2024-12-18 | Open |  |  | Production | No | /sites/PMSystem/Photos/MC-021_78.jpg
ABN-00102 | QR Walk-by |  | MC-008 | VMC MC-01 | CELL-02 | CNC Turning Line B | Machine Shop | Safety device bypassed | Medium | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2024-12-19 | Open |  |  | Maintenance | No | /sites/PMSystem/Photos/MC-008_102.jpg
ABN-00092 | QR Walk-by |  | MC-007 | CNC Lathe TL-05 | CELL-02 | CNC Turning Line B | Machine Shop | Safety device bypassed | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2024-12-22 | Closed | 2025-01-11 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-007_92.jpg
ABN-00181 | QR Walk-by |  | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Oil / coolant leak | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2024-12-31 | Closed | 2025-01-02 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-024_181.jpg
ABN-00179 | QR Walk-by |  | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Oil / coolant leak | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2025-01-07 | Closed | 2025-02-03 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-014_179.jpg
ABN-00004 | PM Checklist | WO-00007 | MC-002 | CNC Lathe TL-02 | CELL-01 | CNC Turning Line A | Machine Shop | Corrosion / rust | Medium | Task 12: Verify E-stop and door interlock function - outside standard (Stops within 1 s) | TECH-03 | Mohammed Rafi | 2025-01-09 | Closed | 2025-01-26 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-002_4.jpg
ABN-00065 | PM Checklist | WO-00229 | MC-027 | Robot Weld Cell RW-01 | CELL-07 | Robotic Welding Bay | Fabrication | Housekeeping / 5S issue | High | Task 9: Weld cell light curtain and door interlock - outside standard (Stops within 1 s) | TECH-08 | Karthik V | 2025-01-09 | Open |  |  | Production | Yes | /sites/PMSystem/Photos/MC-027_65.jpg
ABN-00171 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Damaged guard or cover | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-01-10 | Closed | 2025-02-09 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-003_171.jpg
ABN-00133 | QR Walk-by |  | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Housekeeping / 5S issue | High | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-01-12 | Closed | 2025-02-15 | Rectified during next available window | Production | Yes | /sites/PMSystem/Photos/MC-006_133.jpg
ABN-00066 | PM Checklist | WO-00230 | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Warning lamp / alarm active | Medium | Task 2: Torch / nozzle / contact tip replacement - outside standard (New tip fitted) | TECH-04 | Vignesh S | 2025-01-14 | Closed | 2025-01-16 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-028_66.jpg
ABN-00089 | QR Walk-by |  | MC-033 | Press Feeder PF-01 | CELL-08 | Press Shop | Fabrication | Abnormal noise | High | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2025-01-15 | Closed | 2025-01-25 | Rectified during next available window | Production | Yes | /sites/PMSystem/Photos/MC-033_89.jpg
ABN-00145 | QR Walk-by |  | MC-008 | VMC MC-01 | CELL-02 | CNC Turning Line B | Machine Shop | Safety device bypassed | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2025-01-20 | In Progress |  |  | Safety | No | /sites/PMSystem/Photos/MC-008_145.jpg
ABN-00104 | QR Walk-by |  | MC-033 | Press Feeder PF-01 | CELL-08 | Press Shop | Fabrication | Corrosion / rust | High | Observed during shop floor round - logged via machine QR | TECH-01 | Arun Kumar | 2025-01-21 | Closed | 2025-02-04 | Rectified during next available window | Safety | Yes | /sites/PMSystem/Photos/MC-033_104.jpg
ABN-00088 | QR Walk-by |  | MC-031 | Hyd Press HP-01 | CELL-08 | Press Shop | Fabrication | Warning lamp / alarm active | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-01-25 | Closed | 2025-02-02 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-031_88.jpg
ABN-00037 | PM Checklist | WO-00125 | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Wiring / cable damage | Medium | Task 4: Door seal and curtain condition - outside standard (No gap, no burn-through) | TECH-02 | Suresh Babu | 2025-02-05 | Closed | 2025-03-02 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-014_37.jpg
ABN-00017 | PM Checklist | WO-00060 | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Safety device bypassed | High | Task 6: Spindle vibration check - outside standard (<= 2.8 mm/s RMS) | TECH-01 | Arun Kumar | 2025-02-08 | Closed | 2025-02-20 | Corrective action completed and verified | Production | Yes | /sites/PMSystem/Photos/MC-006_17.jpg
ABN-00193 | QR Walk-by |  | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Corrosion / rust | High | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-02-09 | Closed | 2025-03-09 | Rectified during next available window | Production | Yes | /sites/PMSystem/Photos/MC-004_193.jpg
ABN-00132 | QR Walk-by |  | MC-005 | Chip Conveyor CC-01 | CELL-01 | CNC Turning Line A | Machine Shop | Housekeeping / 5S issue | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-02-25 | Closed | 2025-03-23 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-005_132.jpg
ABN-00082 | QR Walk-by |  | MC-031 | Hyd Press HP-01 | CELL-08 | Press Shop | Fabrication | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2025-03-08 | Closed | 2025-03-14 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-031_82.jpg
ABN-00138 | QR Walk-by |  | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Oil / coolant leak | Medium | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2025-03-11 | Closed | 2025-03-31 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-004_138.jpg
ABN-00025 | PM Checklist | WO-00097 | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Wiring / cable damage | Low | Task 11: Hydraulic power pack pressure and leak check - outside standard (45 - 55 bar, no leak) | TECH-03 | Mohammed Rafi | 2025-03-14 | Closed | 2025-04-02 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-011_25.jpg
ABN-00174 | QR Walk-by |  | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Warning lamp / alarm active | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-03-16 | Closed | 2025-04-17 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-017_174.jpg
ABN-00158 | QR Walk-by |  | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Housekeeping / 5S issue | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-03-17 | Closed | 2025-04-13 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-016_158.jpg
ABN-00026 | PM Checklist | WO-00098 | MC-012 | Gear Shaver GS-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Oil / coolant leak | Low | Task 2: Clean machine bed, swarf tray and coolant filter - outside standard (Filter clear) | TECH-02 | Suresh Babu | 2025-03-18 | Closed | 2025-04-17 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-012_26.jpg
ABN-00027 | PM Checklist | WO-00098 | MC-012 | Gear Shaver GS-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal noise | Low | Task 4: Work spindle bearing temperature - outside standard (<= 60 deg C) | TECH-02 | Suresh Babu | 2025-03-18 | Closed | 2025-03-20 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-012_27.jpg
ABN-00195 | QR Walk-by |  | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Oil / coolant leak | High | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-03-30 | Closed | 2025-04-11 | Rectified during next available window | Production | Yes | /sites/PMSystem/Photos/MC-006_195.jpg
ABN-00173 | QR Walk-by |  | MC-009 | VMC MC-02 | CELL-02 | CNC Turning Line B | Machine Shop | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-04-03 | Closed | 2025-04-22 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-009_173.jpg
ABN-00180 | QR Walk-by |  | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Loose / missing fastener | Low | Observed during shop floor round - logged via machine QR | TECH-01 | Arun Kumar | 2025-04-04 | Closed | 2025-04-12 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-016_180.jpg
ABN-00146 | QR Walk-by |  | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Damaged guard or cover | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-04-06 | Closed | 2025-04-28 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-017_146.jpg
ABN-00191 | QR Walk-by |  | MC-010 | Gear Hobber GH-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Loose / missing fastener | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-04-07 | Closed | 2025-05-07 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-010_191.jpg
ABN-00085 | QR Walk-by |  | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Abnormal noise | Low | Observed during shop floor round - logged via machine QR | TECH-01 | Arun Kumar | 2025-04-09 | Closed | 2025-04-19 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-020_85.jpg
ABN-00130 | QR Walk-by |  | MC-007 | CNC Lathe TL-05 | CELL-02 | CNC Turning Line B | Machine Shop | Air leak | High | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-04-14 | Closed | 2025-05-17 | Rectified during next available window | Safety | Yes | /sites/PMSystem/Photos/MC-007_130.jpg
ABN-00055 | PM Checklist | WO-00192 | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Abnormal noise | Medium | Task 6: Fixture clamp wear and repeatability - outside standard (<= 0.05 mm) | TECH-07 | Ramesh Chandran | 2025-04-16 | Closed | 2025-04-26 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-021_55.jpg
ABN-00143 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Damaged guard or cover | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-04-17 | Closed | 2025-05-26 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-003_143.jpg
ABN-00100 | QR Walk-by |  | MC-002 | CNC Lathe TL-02 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal noise | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-04-19 | Closed | 2025-05-22 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-002_100.jpg
ABN-00005 | PM Checklist | WO-00014 | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Overheating | Medium | Task 6: Air / oil filter condition - outside standard (Clean or replace) | TECH-03 | Mohammed Rafi | 2025-04-23 | Closed | 2025-05-02 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-004_5.jpg
ABN-00056 | PM Checklist | WO-00194 | MC-023 | Assy Conveyor CV-01 | CELL-05 | Assembly Line 1 | Assembly | Overheating | High | Task 9: Electrical panel cleaning and terminal tightness - outside standard (No dust, no loose lug) | TECH-07 | Ramesh Chandran | 2025-04-24 | Closed | 2025-05-21 | Corrective action completed and verified | Safety | Yes | /sites/PMSystem/Photos/MC-023_56.jpg
ABN-00159 | QR Walk-by |  | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Safety device bypassed | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-04-25 | Closed | 2025-06-02 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-029_159.jpg
ABN-00192 | QR Walk-by |  | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Overheating | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-04-25 | Open |  |  | Production | No | /sites/PMSystem/Photos/MC-006_192.jpg
ABN-00123 | QR Walk-by |  | MC-031 | Hyd Press HP-01 | CELL-08 | Press Shop | Fabrication | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-01 | Arun Kumar | 2025-04-27 | Closed | 2025-05-14 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-031_123.jpg
ABN-00106 | QR Walk-by |  | MC-033 | Press Feeder PF-01 | CELL-08 | Press Shop | Fabrication | Safety device bypassed | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-04-28 | Closed | 2025-05-05 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-033_106.jpg
ABN-00101 | QR Walk-by |  | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Loose / missing fastener | High | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-05-04 | Closed | 2025-05-05 | Rectified during next available window | Maintenance | Yes | /sites/PMSystem/Photos/MC-004_101.jpg
ABN-00176 | QR Walk-by |  | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal noise | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-05-06 | Open |  |  | Safety | No | /sites/PMSystem/Photos/MC-011_176.jpg
ABN-00194 | QR Walk-by |  | MC-007 | CNC Lathe TL-05 | CELL-02 | CNC Turning Line B | Machine Shop | Damaged guard or cover | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-05-09 | Closed | 2025-05-26 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-007_194.jpg
ABN-00121 | QR Walk-by |  | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Warning lamp / alarm active | High | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-05-14 | Closed | 2025-05-25 | Rectified during next available window | Production | Yes | /sites/PMSystem/Photos/MC-029_121.jpg
ABN-00038 | PM Checklist | WO-00132 | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Housekeeping / 5S issue | Low | Task 7: Atmosphere gas flow and carbon potential probe - outside standard (Probe mV stable) | TECH-02 | Suresh Babu | 2025-05-15 | Closed | 2025-06-10 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-016_38.jpg
ABN-00177 | QR Walk-by |  | MC-032 | Hyd Press HP-02 | CELL-08 | Press Shop | Fabrication | Abnormal vibration | Medium | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-05-16 | Closed | 2025-06-08 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-032_177.jpg
ABN-00156 | QR Walk-by |  | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Safety device bypassed | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-05-20 | Closed | 2025-06-18 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-021_156.jpg
ABN-00209 | QR Walk-by |  | MC-023 | Assy Conveyor CV-01 | CELL-05 | Assembly Line 1 | Assembly | Warning lamp / alarm active | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-05-25 | Closed | 2025-06-07 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-023_209.jpg
ABN-00110 | QR Walk-by |  | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Overheating | Medium | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2025-05-30 | Closed | 2025-06-04 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-020_110.jpg
ABN-00152 | QR Walk-by |  | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2025-05-31 | Open |  |  | Maintenance | No | /sites/PMSystem/Photos/MC-016_152.jpg
ABN-00210 | QR Walk-by |  | MC-023 | Assy Conveyor CV-01 | CELL-05 | Assembly Line 1 | Assembly | Housekeeping / 5S issue | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-06-05 | Closed | 2025-07-05 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-023_210.jpg
ABN-00165 | QR Walk-by |  | MC-009 | VMC MC-02 | CELL-02 | CNC Turning Line B | Machine Shop | Warning lamp / alarm active | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-06-12 | Closed | 2025-06-25 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-009_165.jpg
ABN-00126 | QR Walk-by |  | MC-007 | CNC Lathe TL-05 | CELL-02 | CNC Turning Line B | Machine Shop | Abnormal noise | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-06-15 | Closed | 2025-07-01 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-007_126.jpg
ABN-00096 | QR Walk-by |  | MC-008 | VMC MC-01 | CELL-02 | CNC Turning Line B | Machine Shop | Abnormal noise | Medium | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-06-26 | Closed | 2025-07-27 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-008_96.jpg
ABN-00081 | QR Walk-by |  | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Oil / coolant leak | Medium | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-06-29 | Closed | 2025-07-13 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-028_81.jpg
ABN-00039 | PM Checklist | WO-00135 | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Damaged guard or cover | Low | Task 5: Quench oil level, temperature and condition - outside standard (Level OK, <= 80 deg C) | TECH-05 | Prakash R | 2025-07-05 | Closed | 2025-07-29 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-014_39.jpg
ABN-00148 | QR Walk-by |  | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Corrosion / rust | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-07-05 | Closed | 2025-07-29 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-029_148.jpg
ABN-00166 | QR Walk-by |  | MC-012 | Gear Shaver GS-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Overheating | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-07-05 | Closed | 2025-08-14 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-012_166.jpg
ABN-00144 | QR Walk-by |  | MC-005 | Chip Conveyor CC-01 | CELL-01 | CNC Turning Line A | Machine Shop | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-07-07 | Closed | 2025-07-16 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-005_144.jpg
ABN-00040 | PM Checklist | WO-00136 | MC-015 | Sealed Quench SQ-02 | CELL-04 | Heat Treatment | Heat Treat | Damaged guard or cover | Medium | Task 10: Cooling water flow and chiller performance - outside standard (>= 60 L/min) | TECH-02 | Suresh Babu | 2025-07-12 | Closed | 2025-08-10 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-015_40.jpg
ABN-00168 | QR Walk-by |  | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Warning lamp / alarm active | Low | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2025-07-16 | Closed | 2025-08-24 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-021_168.jpg
ABN-00041 | PM Checklist | WO-00137 | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Housekeeping / 5S issue | High | Task 5: Quench oil level, temperature and condition - outside standard (Level OK, <= 80 deg C) | TECH-06 | Deepak Nair | 2025-07-18 | Closed | 2025-07-20 | Corrective action completed and verified | Production | Yes | /sites/PMSystem/Photos/MC-016_41.jpg
ABN-00042 | PM Checklist | WO-00138 | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Warning lamp / alarm active | Medium | Task 1: Lock out / tag out verified before start - outside standard (LOTO applied) | TECH-05 | Prakash R | 2025-07-23 | Closed | 2025-07-26 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-017_42.jpg
ABN-00211 | QR Walk-by |  | MC-019 | Assembly Stn AS-01 | CELL-05 | Assembly Line 1 | Assembly | Air leak | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-07-24 | Closed | 2025-08-04 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-019_211.jpg
ABN-00186 | QR Walk-by |  | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-07-26 | Closed | 2025-08-15 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-011_186.jpg
ABN-00043 | PM Checklist | WO-00139 | MC-018 | HT Compressor AC-01 | CELL-04 | Heat Treatment | Heat Treat | Damaged guard or cover | Low | Task 2: General cleaning and housekeeping - outside standard (No debris) | TECH-02 | Suresh Babu | 2025-07-27 | Closed | 2025-08-04 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-018_43.jpg
ABN-00079 | QR Walk-by |  | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-07-28 | Closed | 2025-08-26 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-024_79.jpg
ABN-00107 | QR Walk-by |  | MC-023 | Assy Conveyor CV-01 | CELL-05 | Assembly Line 1 | Assembly | Abnormal vibration | Medium | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2025-08-04 | Closed | 2025-08-25 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-023_107.jpg
ABN-00057 | PM Checklist | WO-00195 | MC-019 | Assembly Stn AS-01 | CELL-05 | Assembly Line 1 | Assembly | Damaged guard or cover | Medium | Task 8: Check station lighting and andon - outside standard (>= 500 lux) | TECH-10 | Naveen Raj | 2025-08-05 | Closed | 2025-08-26 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-019_57.jpg
ABN-00067 | PM Checklist | WO-00236 | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Damaged guard or cover | Medium | Task 4: Bearing greasing as per lube chart - outside standard (All points) | TECH-09 | Sathish Kumar | 2025-08-09 | Closed | 2025-08-24 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-030_67.jpg
ABN-00068 | PM Checklist | WO-00236 | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Abnormal vibration | Low | Task 8: Safety guard and E-stop check - outside standard (Functional) | TECH-09 | Sathish Kumar | 2025-08-09 | Closed | 2025-09-08 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-030_68.jpg
ABN-00094 | QR Walk-by |  | MC-019 | Assembly Stn AS-01 | CELL-05 | Assembly Line 1 | Assembly | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-08-11 | Closed | 2025-08-25 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-019_94.jpg
ABN-00028 | PM Checklist | WO-00101 | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Wiring / cable damage | Low | Task 8: Coolant flow at cutting zone - outside standard (>= 40 L/min) | TECH-01 | Arun Kumar | 2025-08-13 | Closed | 2025-08-30 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-011_28.jpg
ABN-00058 | PM Checklist | WO-00196 | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Safety device bypassed | Low | Task 5: Pneumatic FRL check and drain - outside standard (Bowl clean, no water) | TECH-10 | Naveen Raj | 2025-08-13 | Closed | 2025-09-05 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-020_58.jpg
ABN-00167 | QR Walk-by |  | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Abnormal noise | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-08-14 | Closed | 2025-09-14 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-016_167.jpg
ABN-00150 | QR Walk-by |  | MC-031 | Hyd Press HP-01 | CELL-08 | Press Shop | Fabrication | Abnormal noise | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2025-08-16 | Closed | 2025-08-20 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-031_150.jpg
ABN-00073 | PM Checklist | WO-00254 | MC-032 | Hyd Press HP-02 | CELL-08 | Press Shop | Fabrication | Air leak | Medium | Task 2: Hydraulic oil level, temperature and sample - outside standard (<= 55 deg C, ISO 18/16/13) | TECH-04 | Vignesh S | 2025-08-20 | Closed | 2025-09-18 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-032_73.jpg
ABN-00074 | PM Checklist | WO-00254 | MC-032 | Hyd Press HP-02 | CELL-08 | Press Shop | Fabrication | Loose / missing fastener | High | Task 3: Replace / inspect return-line filter - outside standard (dP indicator green) | TECH-04 | Vignesh S | 2025-08-20 | Closed | 2025-08-21 | Corrective action completed and verified | Production | Yes | /sites/PMSystem/Photos/MC-032_74.jpg
ABN-00075 | PM Checklist | WO-00254 | MC-032 | Hyd Press HP-02 | CELL-08 | Press Shop | Fabrication | Damaged guard or cover | Medium | Task 10: Electrical panel cleaning and terminal tightness - outside standard (No dust, no loose lug) | TECH-04 | Vignesh S | 2025-08-20 | Closed | 2025-08-23 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-032_75.jpg
ABN-00097 | QR Walk-by |  | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Corrosion / rust | Medium | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2025-08-21 | Closed | 2025-09-12 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-020_97.jpg
ABN-00029 | PM Checklist | WO-00103 | MC-013 | Deburring Unit DB-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal vibration | Medium | Task 7: Condensate drain and moisture trap - outside standard (Free draining) | TECH-02 | Suresh Babu | 2025-08-26 | Closed | 2025-09-10 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-013_29.jpg
ABN-00216 | QR Walk-by |  | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Loose / missing fastener | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2025-09-13 | Closed | 2025-09-23 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-017_216.jpg
ABN-00215 | QR Walk-by |  | MC-005 | Chip Conveyor CC-01 | CELL-01 | CNC Turning Line A | Machine Shop | Corrosion / rust | Medium | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-09-16 | Closed | 2025-10-01 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-005_215.jpg
ABN-00021 | PM Checklist | WO-00070 | MC-008 | VMC MC-01 | CELL-02 | CNC Turning Line B | Machine Shop | Housekeeping / 5S issue | Low | Task 2: Clean work enclosure, chip auger and coolant tank - outside standard (No chip accumulation) | TECH-01 | Arun Kumar | 2025-09-20 | Closed | 2025-10-19 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-008_21.jpg
ABN-00022 | PM Checklist | WO-00070 | MC-008 | VMC MC-01 | CELL-02 | CNC Turning Line B | Machine Shop | Overheating | Medium | Task 7: ATC arm alignment and tool clamp force - outside standard (Within OEM spec) | TECH-01 | Arun Kumar | 2025-09-20 | Closed | 2025-09-23 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-008_22.jpg
ABN-00205 | QR Walk-by |  | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Wiring / cable damage | High | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2025-09-20 | Closed | 2025-10-22 | Rectified during next available window | Safety | Yes | /sites/PMSystem/Photos/MC-004_205.jpg
ABN-00184 | QR Walk-by |  | MC-019 | Assembly Stn AS-01 | CELL-05 | Assembly Line 1 | Assembly | Housekeeping / 5S issue | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2025-10-01 | Closed | 2025-10-26 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-019_184.jpg
ABN-00018 | PM Checklist | WO-00068 | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Warning lamp / alarm active | Medium | Task 5: Inspect way covers and wipers for damage - outside standard (No tear / no leak) | TECH-03 | Mohammed Rafi | 2025-10-05 | Closed | 2025-10-24 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-006_18.jpg
ABN-00019 | PM Checklist | WO-00068 | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Air leak | Medium | Task 10: Tailstock / chuck clamping pressure - outside standard (18 - 22 bar) | TECH-03 | Mohammed Rafi | 2025-10-05 | Closed | 2025-10-20 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-006_19.jpg
ABN-00020 | PM Checklist | WO-00068 | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Loose / missing fastener | High | Task 13: Backlash check X and Z axis - outside standard (<= 0.01 mm) | TECH-03 | Mohammed Rafi | 2025-10-05 | Closed | 2025-10-25 | Corrective action completed and verified | Maintenance | Yes | /sites/PMSystem/Photos/MC-006_20.jpg
ABN-00139 | QR Walk-by |  | MC-027 | Robot Weld Cell RW-01 | CELL-07 | Robotic Welding Bay | Fabrication | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2025-10-05 | Open |  |  | Production | No | /sites/PMSystem/Photos/MC-027_139.jpg
ABN-00149 | QR Walk-by |  | MC-008 | VMC MC-01 | CELL-02 | CNC Turning Line B | Machine Shop | Loose / missing fastener | Low | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2025-10-07 | Closed | 2025-10-17 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-008_149.jpg
ABN-00172 | QR Walk-by |  | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2025-10-07 | Closed | 2025-10-28 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-006_172.jpg
ABN-00187 | QR Walk-by |  | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Safety device bypassed | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-10-14 | Closed | 2025-10-21 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-028_187.jpg
ABN-00099 | QR Walk-by |  | MC-015 | Sealed Quench SQ-02 | CELL-04 | Heat Treatment | Heat Treat | Wiring / cable damage | Medium | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-10-17 | Closed | 2025-10-25 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-015_99.jpg
ABN-00091 | QR Walk-by |  | MC-019 | Assembly Stn AS-01 | CELL-05 | Assembly Line 1 | Assembly | Overheating | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2025-11-02 | In Progress |  |  | Maintenance | No | /sites/PMSystem/Photos/MC-019_91.jpg
ABN-00178 | QR Walk-by |  | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2025-11-10 | Closed | 2025-12-17 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-014_178.jpg
ABN-00212 | QR Walk-by |  | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Oil / coolant leak | Low | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-11-11 | Closed | 2025-11-23 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-014_212.jpg
ABN-00105 | QR Walk-by |  | MC-013 | Deburring Unit DB-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Warning lamp / alarm active | Medium | Observed during shop floor round - logged via machine QR | TECH-01 | Arun Kumar | 2025-11-12 | Closed | 2025-11-19 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-013_105.jpg
ABN-00114 | QR Walk-by |  | MC-032 | Hyd Press HP-02 | CELL-08 | Press Shop | Fabrication | Loose / missing fastener | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2025-11-15 | Closed | 2025-12-11 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-032_114.jpg
ABN-00103 | QR Walk-by |  | MC-010 | Gear Hobber GH-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Corrosion / rust | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2025-11-16 | Closed | 2025-12-26 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-010_103.jpg
ABN-00006 | PM Checklist | WO-00023 | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Safety device bypassed | Medium | Task 8: Check hydraulic pressure - outside standard (35 - 40 bar) | TECH-02 | Suresh Babu | 2025-11-18 | Closed | 2025-12-16 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-003_6.jpg
ABN-00044 | PM Checklist | WO-00143 | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Housekeeping / 5S issue | High | Task 1: Lock out / tag out verified before start - outside standard (LOTO applied) | TECH-02 | Suresh Babu | 2025-11-20 | Closed | 2025-12-18 | Corrective action completed and verified | Safety | Yes | /sites/PMSystem/Photos/MC-017_44.jpg
ABN-00007 | PM Checklist | WO-00025 | MC-005 | Chip Conveyor CC-01 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal noise | Medium | Task 9: Electrical panel cleaning and terminal tightness - outside standard (No dust, no loose lug) | TECH-03 | Mohammed Rafi | 2025-11-23 | Closed | 2025-11-25 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-005_7.jpg
ABN-00045 | PM Checklist | WO-00144 | MC-018 | HT Compressor AC-01 | CELL-04 | Heat Treatment | Heat Treat | Overheating | Medium | Task 7: Condensate drain and moisture trap - outside standard (Free draining) | TECH-06 | Deepak Nair | 2025-11-26 | Closed | 2025-12-07 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-018_45.jpg
ABN-00137 | QR Walk-by |  | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2025-11-26 | Closed | 2026-01-02 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-030_137.jpg
ABN-00208 | QR Walk-by |  | MC-005 | Chip Conveyor CC-01 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-11-26 | Closed | 2025-12-28 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-005_208.jpg
ABN-00140 | QR Walk-by |  | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2025-12-08 | Closed | 2025-12-18 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-011_140.jpg
ABN-00185 | QR Walk-by |  | MC-026 | Paint Chiller CH-02 | CELL-06 | Paint & Finishing | Finishing | Abnormal vibration | Medium | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2025-12-09 | Open |  |  | Maintenance | No | /sites/PMSystem/Photos/MC-026_185.jpg
ABN-00151 | QR Walk-by |  | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Safety device bypassed | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2025-12-11 | Closed | 2025-12-19 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-016_151.jpg
ABN-00141 | QR Walk-by |  | MC-002 | CNC Lathe TL-02 | CELL-01 | CNC Turning Line A | Machine Shop | Corrosion / rust | Low | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2025-12-19 | Closed | 2026-01-16 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-002_141.jpg
ABN-00147 | QR Walk-by |  | MC-025 | Curing Oven CO-01 | CELL-06 | Paint & Finishing | Finishing | Oil / coolant leak | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2025-12-29 | Closed | 2026-01-12 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-025_147.jpg
ABN-00207 | QR Walk-by |  | MC-032 | Hyd Press HP-02 | CELL-08 | Press Shop | Fabrication | Housekeeping / 5S issue | Low | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2026-01-02 | Closed | 2026-01-23 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-032_207.jpg
ABN-00059 | PM Checklist | WO-00201 | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Loose / missing fastener | Low | Task 8: Check station lighting and andon - outside standard (>= 500 lux) | TECH-07 | Ramesh Chandran | 2026-01-08 | Closed | 2026-01-27 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-020_59.jpg
ABN-00095 | QR Walk-by |  | MC-033 | Press Feeder PF-01 | CELL-08 | Press Shop | Fabrication | Housekeeping / 5S issue | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2026-01-13 | Closed | 2026-02-16 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-033_95.jpg
ABN-00060 | PM Checklist | WO-00202 | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Loose / missing fastener | Low | Task 5: Pneumatic FRL check and drain - outside standard (Bowl clean, no water) | TECH-07 | Ramesh Chandran | 2026-01-16 | Closed | 2026-01-24 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-021_60.jpg
ABN-00061 | PM Checklist | WO-00202 | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Abnormal noise | Medium | Task 8: Check station lighting and andon - outside standard (>= 500 lux) | TECH-07 | Ramesh Chandran | 2026-01-16 | Closed | 2026-01-21 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-021_61.jpg
ABN-00062 | PM Checklist | WO-00202 | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Housekeeping / 5S issue | Medium | Task 9: Verify E-stop and light curtain - outside standard (Stops within 1 s) | TECH-07 | Ramesh Chandran | 2026-01-16 | In Progress |  |  | Safety | No | /sites/PMSystem/Photos/MC-021_62.jpg
ABN-00080 | QR Walk-by |  | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Air leak | Low | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2026-01-19 | Closed | 2026-02-07 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-006_80.jpg
ABN-00048 | PM Checklist | WO-00148 | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Corrosion / rust | Low | Task 6: Air / oil filter condition - outside standard (Clean or replace) | TECH-06 | Deepak Nair | 2026-01-23 | Closed | 2026-02-14 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-017_48.jpg
ABN-00049 | PM Checklist | WO-00148 | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Damaged guard or cover | Low | Task 9: Electrical panel cleaning and terminal tightness - outside standard (No dust, no loose lug) | TECH-06 | Deepak Nair | 2026-01-23 | Closed | 2026-02-18 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-017_49.jpg
ABN-00153 | QR Walk-by |  | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Safety device bypassed | Low | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2026-01-24 | Closed | 2026-02-14 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-020_153.jpg
ABN-00134 | QR Walk-by |  | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Corrosion / rust | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2026-01-25 | Closed | 2026-02-14 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-028_134.jpg
ABN-00119 | QR Walk-by |  | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2026-02-02 | Closed | 2026-03-09 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-030_119.jpg
ABN-00142 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2026-02-02 | Closed | 2026-03-10 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-003_142.jpg
ABN-00030 | PM Checklist | WO-00104 | MC-010 | Gear Hobber GH-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal noise | Medium | Task 5: Check and top up gearbox oil - outside standard (Between MIN and MAX) | TECH-03 | Mohammed Rafi | 2026-02-04 | Closed | 2026-02-27 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-010_30.jpg
ABN-00135 | QR Walk-by |  | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Air leak | Medium | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2026-02-04 | Closed | 2026-03-12 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-021_135.jpg
ABN-00188 | QR Walk-by |  | MC-033 | Press Feeder PF-01 | CELL-08 | Press Shop | Fabrication | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2026-02-04 | Closed | 2026-03-13 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-033_188.jpg
ABN-00113 | QR Walk-by |  | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Abnormal vibration | Medium | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2026-02-05 | Closed | 2026-02-20 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-024_113.jpg
ABN-00160 | QR Walk-by |  | MC-019 | Assembly Stn AS-01 | CELL-05 | Assembly Line 1 | Assembly | Wiring / cable damage | High | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2026-02-05 | Closed | 2026-03-14 | Rectified during next available window | Maintenance | Yes | /sites/PMSystem/Photos/MC-019_160.jpg
ABN-00064 | PM Checklist | WO-00223 | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Oil / coolant leak | Low | Task 8: Fire suppression and gas detection check - outside standard (System armed, no fault) | TECH-07 | Ramesh Chandran | 2026-02-07 | Closed | 2026-02-13 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-024_64.jpg
ABN-00046 | PM Checklist | WO-00145 | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Wiring / cable damage | Low | Task 2: Thermocouple calibration check (all zones) - outside standard (+/- 3 deg C of master) | TECH-06 | Deepak Nair | 2026-02-08 | Closed | 2026-02-17 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-014_46.jpg
ABN-00047 | PM Checklist | WO-00145 | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Air leak | High | Task 7: Atmosphere gas flow and carbon potential probe - outside standard (Probe mV stable) | TECH-06 | Deepak Nair | 2026-02-08 | Closed | 2026-02-25 | Corrective action completed and verified | Safety | Yes | /sites/PMSystem/Photos/MC-014_47.jpg
ABN-00031 | PM Checklist | WO-00105 | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Damaged guard or cover | Medium | Task 1: Lock out / tag out verified before start - outside standard (LOTO applied) | TECH-02 | Suresh Babu | 2026-02-11 | Closed | 2026-02-21 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-011_31.jpg
ABN-00032 | PM Checklist | WO-00105 | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Air leak | Medium | Task 11: Hydraulic power pack pressure and leak check - outside standard (45 - 55 bar, no leak) | TECH-02 | Suresh Babu | 2026-02-11 | Closed | 2026-03-05 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-011_32.jpg
ABN-00201 | QR Walk-by |  | MC-001 | CNC Lathe TL-01 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal noise | High | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2026-02-13 | Closed | 2026-02-27 | Rectified during next available window | Production | Yes | /sites/PMSystem/Photos/MC-001_201.jpg
ABN-00033 | PM Checklist | WO-00106 | MC-012 | Gear Shaver GS-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Housekeeping / 5S issue | High | Task 6: Inspect timing belts / drive couplings - outside standard (No crack, correct tension) | TECH-01 | Arun Kumar | 2026-02-17 | Closed | 2026-03-13 | Corrective action completed and verified | Safety | Yes | /sites/PMSystem/Photos/MC-012_33.jpg
ABN-00084 | QR Walk-by |  | MC-013 | Deburring Unit DB-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal noise | Low | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2026-02-18 | Closed | 2026-03-10 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-013_84.jpg
ABN-00010 | PM Checklist | WO-00029 | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Oil / coolant leak | High | Task 4: Bearing greasing as per lube chart - outside standard (All points) | TECH-03 | Mohammed Rafi | 2026-02-20 | Closed | 2026-03-18 | Corrective action completed and verified | Maintenance | Yes | /sites/PMSystem/Photos/MC-004_10.jpg
ABN-00011 | PM Checklist | WO-00029 | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Overheating | Medium | Task 7: Condensate drain and moisture trap - outside standard (Free draining) | TECH-03 | Mohammed Rafi | 2026-02-20 | Closed | 2026-03-16 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-004_11.jpg
ABN-00012 | PM Checklist | WO-00030 | MC-005 | Chip Conveyor CC-01 | CELL-01 | CNC Turning Line A | Machine Shop | Overheating | Medium | Task 3: Belt / chain tension and alignment - outside standard (As per OEM) | TECH-02 | Suresh Babu | 2026-02-25 | Closed | 2026-03-21 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-005_12.jpg
ABN-00111 | QR Walk-by |  | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Wiring / cable damage | High | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2026-02-25 | Closed | 2026-03-26 | Rectified during next available window | Safety | Yes | /sites/PMSystem/Photos/MC-024_111.jpg
ABN-00163 | QR Walk-by |  | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2026-03-06 | Closed | 2026-04-05 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-024_163.jpg
ABN-00162 | QR Walk-by |  | MC-017 | Quench Oil Chiller CH-01 | CELL-04 | Heat Treatment | Heat Treat | Loose / missing fastener | High | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2026-03-08 | Closed | 2026-03-18 | Rectified during next available window | Maintenance | Yes | /sites/PMSystem/Photos/MC-017_162.jpg
ABN-00008 | PM Checklist | WO-00026 | MC-001 | CNC Lathe TL-01 | CELL-01 | CNC Turning Line A | Machine Shop | Loose / missing fastener | Medium | Task 3: Check coolant concentration - outside standard (6 - 9 %) | TECH-03 | Mohammed Rafi | 2026-03-09 | Closed | 2026-03-20 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-001_8.jpg
ABN-00009 | PM Checklist | WO-00026 | MC-001 | CNC Lathe TL-01 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal noise | Low | Task 8: Check hydraulic pressure - outside standard (35 - 40 bar) | TECH-03 | Mohammed Rafi | 2026-03-09 | Closed | 2026-03-13 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-001_9.jpg
ABN-00131 | QR Walk-by |  | MC-022 | Leak Test Rig LT-01 | CELL-05 | Assembly Line 1 | Assembly | Overheating | Low | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2026-03-10 | Closed | 2026-04-11 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-022_131.jpg
ABN-00118 | QR Walk-by |  | MC-021 | Assembly Stn AS-03 | CELL-05 | Assembly Line 1 | Assembly | Safety device bypassed | Medium | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2026-03-24 | Closed | 2026-04-27 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-021_118.jpg
ABN-00203 | QR Walk-by |  | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Oil / coolant leak | Medium | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2026-03-29 | Closed | 2026-04-27 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-030_203.jpg
ABN-00050 | PM Checklist | WO-00150 | MC-014 | Sealed Quench SQ-01 | CELL-04 | Heat Treatment | Heat Treat | Abnormal vibration | Low | Task 2: Thermocouple calibration check (all zones) - outside standard (+/- 3 deg C of master) | TECH-05 | Prakash R | 2026-04-06 | Closed | 2026-04-13 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-014_50.jpg
ABN-00090 | QR Walk-by |  | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Wiring / cable damage | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2026-04-11 | Closed | 2026-05-04 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-030_90.jpg
ABN-00122 | QR Walk-by |  | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Housekeeping / 5S issue | Medium | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2026-04-12 | Closed | 2026-05-14 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-028_122.jpg
ABN-00051 | PM Checklist | WO-00152 | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Oil / coolant leak | High | Task 8: Burner flame condition and flame-failure trip test - outside standard (Trips within 3 s) | TECH-06 | Deepak Nair | 2026-04-15 | Closed | 2026-04-25 | Corrective action completed and verified | Maintenance | Yes | /sites/PMSystem/Photos/MC-016_51.jpg
ABN-00125 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal noise | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2026-04-18 | Closed | 2026-05-10 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-003_125.jpg
ABN-00112 | QR Walk-by |  | MC-006 | CNC Lathe TL-04 | CELL-02 | CNC Turning Line B | Machine Shop | Abnormal vibration | Medium | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2026-04-27 | Closed | 2026-05-08 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-006_112.jpg
ABN-00164 | QR Walk-by |  | MC-032 | Hyd Press HP-02 | CELL-08 | Press Shop | Fabrication | Loose / missing fastener | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2026-04-28 | Closed | 2026-05-30 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-032_164.jpg
ABN-00108 | QR Walk-by |  | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Warning lamp / alarm active | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2026-05-07 | Closed | 2026-05-26 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-030_108.jpg
ABN-00116 | QR Walk-by |  | MC-030 | Weld Compressor AC-02 | CELL-07 | Robotic Welding Bay | Fabrication | Safety device bypassed | Medium | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2026-05-09 | Closed | 2026-05-18 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-030_116.jpg
ABN-00013 | PM Checklist | WO-00033 | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal vibration | Low | Task 1: Lock out / tag out verified before start - outside standard (LOTO applied) | TECH-03 | Mohammed Rafi | 2026-05-13 | Closed | 2026-05-24 | Corrective action completed and verified | Maintenance | No | /sites/PMSystem/Photos/MC-003_13.jpg
ABN-00155 | QR Walk-by |  | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-09 | Sathish Kumar | 2026-05-17 | Closed | 2026-06-09 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-028_155.jpg
ABN-00093 | QR Walk-by |  | MC-024 | Paint Booth PB-01 | CELL-06 | Paint & Finishing | Finishing | Abnormal noise | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2026-05-21 | Closed | 2026-05-30 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-024_93.jpg
ABN-00169 | QR Walk-by |  | MC-005 | Chip Conveyor CC-01 | CELL-01 | CNC Turning Line A | Machine Shop | Air leak | Low | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2026-05-22 | Closed | 2026-06-14 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-005_169.jpg
ABN-00190 | QR Walk-by |  | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Safety device bypassed | High | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2026-05-24 | Closed | 2026-06-08 | Rectified during next available window | Safety | Yes | /sites/PMSystem/Photos/MC-028_190.jpg
ABN-00189 | QR Walk-by |  | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Oil / coolant leak | Low | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2026-05-27 | Closed | 2026-06-24 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-028_189.jpg
ABN-00196 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Housekeeping / 5S issue | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2026-06-03 | Closed | 2026-07-03 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-003_196.jpg
ABN-00109 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Air leak | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2026-06-04 | Closed | 2026-07-13 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-003_109.jpg
ABN-00070 | PM Checklist | WO-00243 | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Corrosion / rust | High | Task 1: Lock out / tag out verified before start - outside standard (LOTO applied) | TECH-09 | Sathish Kumar | 2026-06-19 | In Progress |  |  | Production | Yes | /sites/PMSystem/Photos/MC-029_70.jpg
ABN-00071 | PM Checklist | WO-00243 | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Loose / missing fastener | Medium | Task 4: Bearing greasing as per lube chart - outside standard (All points) | TECH-09 | Sathish Kumar | 2026-06-19 | Closed | 2026-07-14 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-029_71.jpg
ABN-00072 | PM Checklist | WO-00243 | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Warning lamp / alarm active | Low | Task 6: Air / oil filter condition - outside standard (Clean or replace) | TECH-09 | Sathish Kumar | 2026-06-19 | Closed | 2026-07-19 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-029_72.jpg
ABN-00063 | PM Checklist | WO-00208 | MC-022 | Leak Test Rig LT-01 | CELL-05 | Assembly Line 1 | Assembly | Oil / coolant leak | Medium | Task 3: Torque tool calibration verification - outside standard (+/- 3 % of setpoint) | TECH-10 | Naveen Raj | 2026-06-20 | Closed | 2026-07-17 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-022_63.jpg
ABN-00023 | PM Checklist | WO-00079 | MC-009 | VMC MC-02 | CELL-02 | CNC Turning Line B | Machine Shop | Overheating | Low | Task 3: Check coolant concentration - outside standard (6 - 9 %) | TECH-02 | Suresh Babu | 2026-06-23 | Closed | 2026-07-12 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-009_23.jpg
ABN-00024 | PM Checklist | WO-00079 | MC-009 | VMC MC-02 | CELL-02 | CNC Turning Line B | Machine Shop | Warning lamp / alarm active | Low | Task 9: Verify axis home position repeatability - outside standard (<= 0.005 mm) | TECH-02 | Suresh Babu | 2026-06-23 | Closed | 2026-07-07 | Corrective action completed and verified | Safety | No | /sites/PMSystem/Photos/MC-009_24.jpg
ABN-00117 | QR Walk-by |  | MC-007 | CNC Lathe TL-05 | CELL-02 | CNC Turning Line B | Machine Shop | Oil / coolant leak | Low | Observed during shop floor round - logged via machine QR | TECH-01 | Arun Kumar | 2026-07-04 | Closed | 2026-07-29 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-007_117.jpg
ABN-00175 | QR Walk-by |  | MC-029 | Positioner PZ-01 | CELL-07 | Robotic Welding Bay | Fabrication | Abnormal noise | Medium | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2026-07-04 | Closed | 2026-08-04 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-029_175.jpg
ABN-00069 | PM Checklist | WO-00242 | MC-028 | Robot Weld Cell RW-02 | CELL-07 | Robotic Welding Bay | Fabrication | Oil / coolant leak | Medium | Task 4: Shielding gas flow and leak check - outside standard (15 - 20 L/min) | TECH-04 | Vignesh S | 2026-07-06 | Closed | 2026-07-21 | Corrective action completed and verified | Production | No | /sites/PMSystem/Photos/MC-028_69.jpg
ABN-00034 | PM Checklist | WO-00108 | MC-010 | Gear Hobber GH-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Oil / coolant leak | High | Task 6: Inspect timing belts / drive couplings - outside standard (No crack, correct tension) | TECH-01 | Arun Kumar | 2026-07-08 | Closed | 2026-08-05 | Corrective action completed and verified | Safety | Yes | /sites/PMSystem/Photos/MC-010_34.jpg
ABN-00052 | PM Checklist | WO-00156 | MC-015 | Sealed Quench SQ-02 | CELL-04 | Heat Treatment | Heat Treat | Warning lamp / alarm active | High | Task 2: Thermocouple calibration check (all zones) - outside standard (+/- 3 deg C of master) | TECH-06 | Deepak Nair | 2026-07-11 | Closed | 2026-07-16 | Corrective action completed and verified | Production | Yes | /sites/PMSystem/Photos/MC-015_52.jpg
ABN-00035 | PM Checklist | WO-00109 | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Damaged guard or cover | Medium | Task 2: Clean machine bed, swarf tray and coolant filter - outside standard (Filter clear) | TECH-03 | Mohammed Rafi | 2026-07-15 | In Progress |  |  | Safety | No | /sites/PMSystem/Photos/MC-011_35.jpg
ABN-00036 | PM Checklist | WO-00109 | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Abnormal vibration | Medium | Task 4: Work spindle bearing temperature - outside standard (<= 60 deg C) | TECH-03 | Mohammed Rafi | 2026-07-15 | Open |  |  | Safety | No | /sites/PMSystem/Photos/MC-011_36.jpg
ABN-00206 | QR Walk-by |  | MC-019 | Assembly Stn AS-01 | CELL-05 | Assembly Line 1 | Assembly | Warning lamp / alarm active | Medium | Observed during shop floor round - logged via machine QR | TECH-10 | Naveen Raj | 2026-07-21 | Closed | 2026-08-30 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-019_206.jpg
ABN-00154 | QR Walk-by |  | MC-027 | Robot Weld Cell RW-01 | CELL-07 | Robotic Welding Bay | Fabrication | Air leak | Medium | Observed during shop floor round - logged via machine QR | TECH-08 | Karthik V | 2026-07-24 | Closed | 2026-08-20 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-027_154.jpg
ABN-00120 | QR Walk-by |  | MC-002 | CNC Lathe TL-02 | CELL-01 | CNC Turning Line A | Machine Shop | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2026-07-26 | Open |  |  | Production | No | /sites/PMSystem/Photos/MC-002_120.jpg
ABN-00087 | QR Walk-by |  | MC-016 | Tempering Furnace TF-01 | CELL-04 | Heat Treatment | Heat Treat | Housekeeping / 5S issue | High | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2026-07-29 | Closed | 2026-08-22 | Rectified during next available window | Safety | Yes | /sites/PMSystem/Photos/MC-016_87.jpg
ABN-00098 | QR Walk-by |  | MC-020 | Assembly Stn AS-02 | CELL-05 | Assembly Line 1 | Assembly | Warning lamp / alarm active | Low | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2026-07-29 | Closed | 2026-08-08 | Rectified during next available window | Safety | No | /sites/PMSystem/Photos/MC-020_98.jpg
ABN-00077 | QR Walk-by |  | MC-013 | Deburring Unit DB-01 | CELL-03 | Gear Cutting Cell | Machine Shop | Corrosion / rust | High | Observed during shop floor round - logged via machine QR | TECH-02 | Suresh Babu | 2026-08-04 | Open |  |  | Production | Yes | /sites/PMSystem/Photos/MC-013_77.jpg
ABN-00161 | QR Walk-by |  | MC-002 | CNC Lathe TL-02 | CELL-01 | CNC Turning Line A | Machine Shop | Abnormal vibration | Low | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2026-08-04 | In Progress |  |  | Maintenance | No | /sites/PMSystem/Photos/MC-002_161.jpg
ABN-00128 | QR Walk-by |  | MC-011 | Gear Hobber GH-02 | CELL-03 | Gear Cutting Cell | Machine Shop | Housekeeping / 5S issue | Low | Observed during shop floor round - logged via machine QR | TECH-07 | Ramesh Chandran | 2026-08-07 | Closed | 2026-09-09 | Rectified during next available window | Production | No | /sites/PMSystem/Photos/MC-011_128.jpg
ABN-00129 | QR Walk-by |  | MC-018 | HT Compressor AC-01 | CELL-04 | Heat Treatment | Heat Treat | Wiring / cable damage | Low | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2026-08-07 | Open |  |  | Production | No | /sites/PMSystem/Photos/MC-018_129.jpg
ABN-00204 | QR Walk-by |  | MC-031 | Hyd Press HP-01 | CELL-08 | Press Shop | Fabrication | Loose / missing fastener | Low | Observed during shop floor round - logged via machine QR | TECH-04 | Vignesh S | 2026-08-07 | Open |  |  | Production | No | /sites/PMSystem/Photos/MC-031_204.jpg
ABN-00214 | QR Walk-by |  | MC-004 | Bar Feeder BF-01 | CELL-01 | CNC Turning Line A | Machine Shop | Oil / coolant leak | Medium | Observed during shop floor round - logged via machine QR | TECH-03 | Mohammed Rafi | 2026-08-09 | Closed | 2026-09-11 | Rectified during next available window | Maintenance | No | /sites/PMSystem/Photos/MC-004_214.jpg
ABN-00170 | QR Walk-by |  | MC-003 | CNC Lathe TL-03 | CELL-01 | CNC Turning Line A | Machine Shop | Wiring / cable damage | Medium | Observed during shop floor round - logged via machine QR | TECH-05 | Prakash R | 2026-08-22 | In Progress |  |  | Maintenance | No | /sites/PMSystem/Photos/MC-003_170.jpg
ABN-00076 | PM Checklist | WO-00258 | MC-033 | Press Feeder PF-01 | CELL-08 | Press Shop | Fabrication | Housekeeping / 5S issue | High | Task 2: General cleaning and housekeeping - outside standard (No debris) | TECH-09 | Sathish Kumar | 2026-08-24 | Open |  |  | Production | Yes | /sites/PMSystem/Photos/MC-033_76.jpg
ABN-00157 | QR Walk-by |  | MC-009 | VMC MC-02 | CELL-02 | CNC Turning Line B | Machine Shop | Housekeeping / 5S issue | Medium | Observed during shop floor round - logged via machine QR | TECH-06 | Deepak Nair | 2026-08-24 | Open |  |  | Maintenance | No | /sites/PMSystem/Photos/MC-009_157.jpg