BUILD — how to build and run this system, start to finish

Cell-Based PM Planning, Scheduling & Tracking System

Eaton Power Quality Pvt Ltd  ·  Pondicherry  ·  Maintenance Engineering

SharePoint Online  ·  Microsoft Forms  ·  Power Automate  ·  Power BI

No additional licence required

Read this first. It is the only document you need open to build the system. Everything else is detail you go and fetch when a step tells you to.

| What you are building | A preventive-maintenance system for EPQPL Pondicherry: 8 cells, 30 machines, PM triggered per cell at 4,000 accumulated standard hours with a 6-month calendar backstop |
| --- | --- |
| Runs on | SharePoint Online, Power Automate, Microsoft Forms, Power BI — all Microsoft 365 E3, no extra licence |
| Total effort | About 6 working days, one person |
| Prerequisites | A SharePoint site you own, PowerShell 7, Python 3.9+ |

## The six stages

| # | Stage | Time | You end with |
| --- | --- | --- | --- |
| 0 | [Set up your machine](#stage-0) | 30 min | Tools installed, checks passing |
| 1 | [Prepare and validate the data](#stage-1) | 2 h | 14 CSVs, 0 errors |
| 2 | [Provision SharePoint](#stage-2) | 3 h | 14 lists, 138 columns, 11 views, 5 libraries, data loaded |
| 3 | [Build the forms](#stage-3) | 4 h | 5 Forms, pre-filled links wired into the Machine Hub |
| 4 | [Print and fit the QR stickers](#stage-4) | 4 h | 30 stickers on machines, every one scan-tested |
| 5 | [Build the flows](#stage-5) | 2 days | 9 automations running unattended |
| 6 | [Publish Power BI, test, go live](#stage-6) | 1.5 days | 9-page dashboard, 36 UAT cases signed off |

Do the stages in order. Stage 5 cannot be built before Stage 3 exists, because a flow's trigger has nothing to point at.

## The one decision to make before you start

Who owns this? Every flow and every form is created under one Microsoft 365 account, and that account's connections are what the flows run on.

There is no service account available, so it will be an individual's account. That works, but understand what it means: if that account is ever disabled or loses its licence, every connection breaks and all nine flows stop — regardless of who else you add as a co-owner. Co-ownership shortens the repair; it does not prevent the failure.

Pick someone who is not about to change role. Add two co-owners to every flow as you build it. And know the warning sign, which is built into the system: the daily digest sends a one-line "PM system healthy" every Monday even when nothing is wrong. No digest on a Monday means the flows have stopped.

Full reasoning and the reassignment procedure: docs/ASSUMPTIONS.md §8.2.

<a name="stage-0"></a>

## Stage 0 — Set up your machine · 30 minutes

### Install three things

# 1. Python 3.9 or newer - check what you have

python3 --version

# 2. Python packages

pip install -r tools/requirements.txt

pip install -r qr/requirements.txt

# 3. PowerShell 7 and the SharePoint module

#    Download PowerShell 7 from Microsoft, then:

Install-Module PnP.PowerShell -Scope CurrentUser

`pyzbar` needs a system library. On Debian/Ubuntu: sudo apt install libzbar0.

Without it the QR round-trip test falls back to a weaker check, and that test is

the thing standing between you and 30 wrong stickers.

Node.js is optional. It only regenerates the Word files and the licence deck, and both are already built in docs/. If you want to regenerate them: npm install.

### Prove the project is intact

python3 tools/check_consistency.py

This checks 36 things — that the schema, the exported data, the Power BI model, the flow specifications, the views and every document all agree with each other. It must print:

Everything agrees. Schema, data, model, flows, views and documents.

If it does not, stop and read what it says. It names the file and the line.

<a name="stage-1"></a>

## Stage 1 — Prepare and validate the data · 2 hours

What you are doing: turning the three supplied workbooks into typed, validated CSVs that SharePoint can accept, and proving the data is sound before it goes anywhere.

python3 tools/prepare_sharepoint_data.py --strict

It must end with `0 error(s), 0 warning(s)`. With --strict it refuses to write anything if it finds a problem, which is the point — a half-valid load is far harder to unpick than a rejected one.

You get 14 files in sharepoint/data/, plus _VALIDATION_REPORT.md (read it) and _ROW_COUNTS.csv (keep it; you reconcile against it in Stage 2).

Expect 2,422 rows across 14 lists. 730 of them are the plant calendar.

### What it is actually checking

Six integrity rules that the business depends on, not just column types:

- Every primary key is present and unique

- A work order's machine-task count equals its Machines_In_Scope

- A work order is only Completed when no task is still open

- The counter reset moves all three cell fields together, or not at all

- Every checklist response has a parent machine task

- A completed work order has at least one scanned-out task — without one, nothing can date it, and it vanishes silently from three measures that all read *better* for its absence

<a name="stage-2"></a>

## Stage 2 — Provision SharePoint · 3 hours

What you are doing: creating the lists, columns, indexes, views and libraries, then loading the data.

### 2.1 Dry-run everything first

All three scripts support -WhatIf, which shows you exactly what they would do without touching the tenant.

cd sharepoint

.\provision_lists.ps1 -SiteUrl "https://yourcompany.sharepoint.com/sites/Maintenance" -WhatIf

⚠ If it fails asking for admin approval

Many corporate tenants block unapproved applications, and the error does not tell

you what to do. Someone with Entra (Azure AD) rights registers one, once:

```powershell

Register-PnPEntraIDAppForInteractiveLogin `

-ApplicationName "EPQPL PM Provisioning" `

-Tenant yourcompany.onmicrosoft.com -Interactive

```

It prints a client id. Pass it as -ClientId "<id>" to all three scripts from

then on.

Confirm this before provisioning day. It is ten minutes for whoever holds the

rights, and half a day lost if you discover it at 9 a.m. on the morning.

### 2.2 Run for real, in this order

.\provision_lists.ps1 -SiteUrl "<your site>"      # 14 lists, 138 columns, 5 libraries

.\apply_views.ps1     -SiteUrl "<your site>"      # 11 views + shop-floor formatting

.\load_data.ps1       -SiteUrl "<your site>" -WhatIf   # dry run first

.\load_data.ps1       -SiteUrl "<your site>"      # 2,422 rows

Then reconcile. Open each list and compare its item count against sharepoint/data/_ROW_COUNTS.csv. A list short by even one row means a row was dropped silently — find it now, not in six months.

### 2.3 Two things to check before moving on

Column internal names must not be mangled. Open Cell_Master → List settings → click Cell_ID and read the browser URL. It must say Field=Cell_ID, not Field=Cell%5Fx005f%5FID. If it is mangled, the Power BI model will load blank columns and you will not know why. The field XML sets Name, StaticName and DisplayName identically to prevent exactly this.

Mark your holidays. Open Plant_Calendar and set Is_Working_Day = No for Pongal, Diwali and any plant shutdown. This list is the divisor in the mid-month proration rule. Maintain it every December for the year ahead — if it runs out, the monthly import terminates rather than dividing by zero.

<a name="stage-3"></a>

## Stage 3 — Build the forms · 4 hours

What you are doing: building the five Microsoft Forms the technicians fill in. This is the fiddliest stage. Take your time.

Every question on every form, with the column it lands in, is in `automate/FLOW_SPECS.md` §"The five forms". Build from there, not from memory.

| # | Form | Questions | Machine Hub button |
| --- | --- | --- | --- |
| 1 | PM Start | 2, both pre-filled | ▶ START PM |
| 2 | PM Checklist | 4 + nine branched sections | ☑ COMPLETE CHECKLIST |
| 3 | Spare Replaced | 9 | 🔧 SPARE FITTED |
| 4 | Breakdown Report | 14 | ⚠ REPORT BREAKDOWN |
| 5 | Abnormality Log | 9 | 👁 LOG ABNORMALITY |

### ⚠ The rule that will catch you out

A pre-filled link fills answers by POSITION, not by name.

So on every form Machine ID is question 1 and Cell ID is question 2 — and on the checklist, Checklist ID is question 3. Insert anything above them and every sticker on the shop floor starts filling the wrong boxes, silently, with no error. New questions go at the bottom, always.

### Settings, identical on all five

- Anyone can respond ✅ — the handsets share one login

- Record name ❌ — it would record the shared account, which looks like attribution and is not

- Technician Name is a mandatory Choice, typed out from Technician_Master. Never a text box: free text gives you "Murugan", "murugan s" and "MURUGAN S", and then nothing can be counted.

  - The one exception is PM Start, which asks nothing at all. Nothing stores who started a job — Completed_By on the checklist is the record that matters — so a dropdown there would be a tap that throws its answer away.

### Then wire up the Machine Hub — 11 placeholders, set once

For each form: Collect responses → Get a link to prefill answers, fill in MC-01-001 and CELL-01, and Get link. You get something like:

https://forms.office.com/r/AbCdEf?id=xxxxx&r1a2b3c4=MC-01-001&r5d6e7f8=CELL-01

Cut it in two and paste the halves into sharepoint/formatting/Machine_Master.MachineHub.view.json:

| Placeholder | What to paste |
| --- | --- |
| FORM_<NAME>_UPTO_MACHINE | everything before the machine ID |
| FORM_<NAME>_UPTO_CELL | the next key with its & and = |
| FORM_CHECKLIST_UPTO_CLID | the checklist form's third key |

Copy and paste both halves out of a real link. Retyping an eight-character question id by hand gives you a button that opens the form with nothing filled in, and nothing about it looks wrong until somebody uses it.

Then re-run .\apply_views.ps1 -SiteUrl "<your site>" to push the formatting up.

Test one on a real phone before you go on. The first thing you touch should be a real question — not the keyboard.

<a name="stage-4"></a>

## Stage 4 — Print and fit the QR stickers · 4 hours

python3 qr/generate_qr_labels.py --base-url https://yourcompany.sharepoint.com/sites/Maintenance --test

It must say `passed: 30    failed: 0`. If it does not, do not print. --test reads every sticker back with a scanner and checks it points at its own machine. A wrong sticker takes about a month to notice, and by then it has been scanned two hundred times against the wrong machine.

Print qr/labels/PM_QR_Labels.pdf:

| Setting | Value | Why |
| --- | --- | --- |
| Paper | Polyester or vinyl, 3 × 8 pre-cut at 50 × 30 mm | Paper does not survive a fuse plant — oil soaks in and the code is gone in weeks |
| Scale | 100% / Actual size | "Fit to page" shrinks the code below what a phone reads reliably |
| Printer | Laser, not inkjet | Inkjet runs the moment someone wipes the machine with solvent |

Stick them at chest height, flat, away from coolant spray.

Then walk the floor and scan every single one. Two people, one hour. This removes an entire class of problem permanently.

<a name="stage-5"></a>

## Stage 5 — Build the flows · 2 days

What you are doing: building the nine automations that make the system run by itself. This is the biggest stage.

Open automate/FLOW_SPECS.md — every flow, every action in order, every setting. automate/expressions.md has every formula written out to copy and paste.

### Build in this order

| Order | Flow | What it does | Time |
| --- | --- | --- | --- |
| 1st | PM-05 Cell Closure & Reset | Zeroes the counter when the last machine in a cell is done | 3 h |
| 2nd | PM-02 PM Trigger | Raises the work order at 4,000 hours or 6 months | 3 h |
| 3rd | PM-01 Monthly Hours Import | Adds each month's hours to the counters | 4 h |
| then | PM-03, PM-04 | Scan in, checklist submission | 4 h |
| then | PM-06, PM-07, PM-08 | Breakdown, spare fitted, abnormality | 3 h |
| last | PM-09 | Daily digest | 2 h |

Flows 5, 2 and 1 are the spine. Get those three working before anything else.

### Three rules that will each save you a day

1. Rename actions before you write expressions. Expressions reference actions by name with spaces replaced by underscores. Rename an action afterwards and the expression breaks — the flow still saves, then fails at runtime with a null.

2. Turn concurrency OFF on flows 1 and 5. Both touch the running counter. Two parallel runs would read the same value and one increment would be lost.

3. Route failure alerts to a shared mailbox, not the owner's inbox. The built-in "email me if a flow fails" reaches the owner only, which is no use the day the owner's account is the thing that broke.

And add your two co-owners to each flow as you build it. Doing it later across nine flows is an hour nobody ever schedules.

<a name="stage-6"></a>

## Stage 6 — Power BI, UAT, go live · 1.5 days

### 6.1 Open and repoint the report

Open powerbi/PM_Dashboard.pbip in Power BI Desktop. Home → Transform data → Manage parameters, set pSourceMode to SharePoint and pSiteUrl to your site. Refresh.

The whole model swaps source through one function (fnGetTable), so this is a parameter change, not a rebuild.

One thing to finish by hand: on page 5, select Machine 360 and drag Dim_Machine[Machine_ID] into the Drill through well. It cannot be expressed in the file format. It takes under a minute.

### 6.2 Cross-check the numbers

python3 tools/verify_measures.py

This recomputes 65 measures in plain Python, independently of the DAX, from the same source data. Compare against the dashboard. Two independent derivations agreeing is a check; one reading back what the other stored is not.

Spot-check these four by hand:

| Measure | Expected on the supplied data |
| --- | --- |
| Breakdowns After PM (7d) | 7 of 88 (8.0%) |
| PM Compliance % | 89.6% (43 of 48) |
| Reset Not Applied Count | 0 |
| Schedule Adherence % | 54.9% (28 of 51 committed rows) |

### 6.3 UAT — all 36 cases

docs/UAT_TEST_CASES.md, in order. Record a name and a date against each; an unrecorded test is an untested system. Test on a separate SharePoint site — several cases deliberately corrupt data to prove a guard works.

The six that must pass before go-live:

| Case | What it proves |
| --- | --- |
| UAT-03 | A cell crossing 4,000 raises exactly one work order |
| UAT-07 | The 6-month backstop fires for a low-utilisation cell |
| UAT-14 | Three of four machines complete and nothing resets |
| UAT-15 | The fourth completes and all three cell fields move together |
| UAT-19 | A mid-month reset prorates by working days to 720.00 h |
| UAT-30a | The Monday heartbeat arrives on a clean week |

UAT-14 and UAT-15 together are the whole system. If the counter resets at three of four, every PM interval is wrong from that day on and no dashboard will tell you.

### 6.4 Train and go live

- Technicians, 30 min: scan, start, checklist, submit. Why the name dropdown matters — it is the only record of who did the work. (docs/TECHNICIAN_SOP_1PAGE.md is a bilingual one-pager to print and laminate at every cell.)

- Supervisors, 1 h: the allotted list, the daily digest, the NOT OK Findings view and deciding which findings become work orders.

- Go live on a Monday, not a Friday. Run the first monthly upload with someone watching.

## The five commands that prove it still works

Run these any time you change something. All five should be clean.

python3 tools/check_consistency.py          # 36 checks: everything agrees

python3 tools/prepare_sharepoint_data.py --strict   # 0 errors, 0 warnings, 2,422 rows

python3 tools/validate_model.py             # 0 errors: every reference resolves

python3 tools/verify_measures.py            # 65 measures, none blank

python3 qr/generate_qr_labels.py --test     # 30/30 optical decode

## Where everything lives

BUILD.md                    <- you are here

README.md                   what this is, in one page

docs/

STEP_BY_STEP_GUIDE.md     the plain-English walkthrough (also .docx)

HANDOVER.md               the single hand-over summary  (also .docx)

IMPLEMENTATION_RUNBOOK.md the same steps, full technical detail

DATA_DICTIONARY.md        every one of the 138 columns, and why it exists

ASSUMPTIONS.md            every judgement call, with verified figures

UAT_TEST_CASES.md         36 cases

TECHNICIAN_SOP_1PAGE.md   bilingual shop-floor sheet, print and laminate

POWERAPPS_LICENCE_CASE.pptx   business case for the Phase 2 canvas app

sharepoint/

provision_lists.ps1       14 lists, 138 columns, indexes, 5 libraries

apply_views.ps1           11 views + shop-floor column formatting

load_data.ps1             batched CSV load with type conversion

schema/                   one JSON per list — what the scripts read

views/, formatting/       view definitions and the Machine Hub card

data/                     import-ready CSVs, validation report, row counts

automate/

FLOW_SPECS.md             5 forms and 9 flows, action by action

expressions.md            every expression, copy-paste ready

powerbi/

PM_Dashboard.pbip         open this in Power BI Desktop

m_queries/                20 commented Power Query scripts

dax/measures.dax          85 measures, each with a comment

qr/generate_qr_labels.py    --test decodes every label back to its own machine

tools/                      data prep, schema generation, and the five checks

powerapps/                  Phase 2 — specified and costed, not licensed

input/                      the three supplied workbooks, unmodified

## What this system deliberately does not record

Four things. None is recoverable from history, so if one matters, reinstate it before go-live, not after — docs/ASSUMPTIONS.md §10 has the full reasoning.

- The scan that led nowhere — a QR scan against a machine with no open work order. The technician is still told; the fact is no longer filed. This is the first thing to bring back if take-up is ever in doubt.

- Spare approval lead time and stock at the moment of asking — the requisition loop was removed because the stores process already runs it.

- **Who *started* a PM**, as distinct from who finished it.

- Make, model and year installed — asset-register detail.